| Unit title | Managing an Event |  | Key to learning opportunities |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Guided learning hours | 90 |  | AW | Assignment writing | AW | Revision session |
| Number of lessons | 90 |  | GS | Guest speaker | GS | Visit |
| Duration of lessons | 1 hour (unless otherwise stated) |  | IS | Independent study | IS | Work experience |
| Links to other units |  |  |  |  |  |  |
| - Unit 9: Team Building in Business - Unit 14: Investigating Customer Service - Unit 19: Pitching for a New Business - Unit 33: Supply Chain Operations |  |  |  |  |  |  |

| Lesson | Topic | Lesson type | Suggested activities | Classroom resources |
| --- | --- | --- | --- | --- |
| Learning aim A: Explore the role of an event organiser |  |  |  |  |
| 1 | Unit introduction |  | - Tutor presentation: Issue specifications to discuss the unit, the learning outcomes, and the mode of assessment. - Tutor presentation: Split learners into small groups (no more than six people). These groups will be the working group to stage and manage the event. - Small group activity; class discussion: Ask learners to collaborate in small groups to come up with examples of different events they have experience of, then use these as the basis for a class discussion. | - Tutor presentation and notes - Small dry wipe boards for group activity |
| 2 | Topic A.1 Tasks to be completed - Organising: venue, location, catering, planning and reserving facilities, e.g. toilets if outdoor event, setting up programme, preparing and distributing documents, contracts. | IS | - Tutor presentation: Describe factors that an event organiser would need to take into consideration when organising an event. - Paired practical activity: Learners research and prepare questions ahead of the guest speaker visit. | - Tutor presentation and notes - PC or laptops for preparing questions |
| 3 | Topic A.1 Tasks to be completed - Organising: venue, location, catering, planning and reserving facilities, e.g. toilets if outdoor event, setting up programme, preparing and distributing documents, contracts. | GS | - Guest speaker: Enlist the help of a visiting speaker, such as someone from a local charity with the responsibility of organising fund-raising events, to explain the skills that they need to organise events and the tasks involved. - Class discussion: Question and answer session with the speaker using prepared questions. | - Notepads/pens for taking notes |
| 4 | Topic A.1 Tasks to be completed - Organising venue, location, catering, planning and reserving facilities, e.g. toilets if outdoor event, setting up programme, preparing and distributing documents, contracts. | IS | - Tutor-led discussion: Recap on factors to be taken into account when organising an event. - Small group activity: Each group should carry out research into possible venues and locations for their events. They should prepare a table showing the pros and cons of each, and should take costs into account. | - PC or laptops with internet connection for research |
| 5 | Topic A.1 Tasks to be completed - Investigating current legal requirements, including consumer protection. |  | - Tutor presentation: Legal requirements, including consumer protection and health and safety. - Class discussion: Learners discuss events that they have attended, identifying and giving examples of how the legal requirements were met by the organisers. | - Tutor presentation and notes |
| 6 | Topic A.1 Tasks to be completed - Setting up organisational procedures, e.g. risk assessment and security. |  | - Tutor presentation: Risk assessments – show samples of different risk assessments for different situations. - Small group activity: Groups of learners carry out a risk assessment for a given situation. | - Tutor presentation and notes - Samples of risk assessments |
| 7 | Topic A.2 Different skills needed by an effective event organiser - Organisational. - Problem solving. - Time management. - Negotiation. - Communication. - Interpersonal. | IS | - Tutor-led discussion: Discuss planning skills needed to organise an event. Use whiteboard to write up skills identified by class. - Individual activity: Learners should prepare a list of their personal skills, giving examples of when each skill has been used. Identify any gaps in the list. | - Whiteboard |
| 8 | Topic A.3 Common formats for skills audit collection - Likert scale. - Semantic differential scale. - Observation. - Questionnaire. - Appraisal. | IS | - Tutor presentation: Purposes of skills audits – different formats used for skills audit collection. - Paired activity: Learners conduct research into different skills audit collection formats. - Class discussion: The appropriate formats to use for individual learners’ skills audits. | - Tutor presentation and notes - Computers/laptops with internet access |
| 9 | Topic A.3 Formats for skills audits collection - Likert scale. - Semantic differential scale. - Observation. - Questionnaire. - Appraisal. | IS | - Individual activity: Complete an individual skills audit, highlighting any gaps in skills required to be an event organiser. | - Copy of blank skills audit |
| 10–15 |  | AW | - Assignment writing: Complete assignment 1. | - Assignment brief |

| Learning aim B: Investigate the feasibility of a proposed event |  |  |  |  |
| --- | --- | --- | --- | --- |
| 16–17 | Topic B.1 Different types of event, and the factors affecting success - Business events: conferences, exhibitions, product launches, trade shows, shareholders’ meetings, press conferences, awards evenings, team building, seminars. - Sport and recreation events: the Olympics, the Commonwealth Games, sports tournaments, sports matches, motor sports events, racing, equestrian events, country fairs, food festivals, fun runs, village fetes, sailing regattas, dog shows, collectors’ fairs. - Entertainment: music festivals, concerts, plays. - Celebrations: examples include Christmas, weddings, prom nights, birthdays. - Social enterprise events: charity sports events, charity fund raising events, e.g. dinners, galas, auctions. | IS | - Tutor-led discussion: Direct a discussion on different types of events, and learners’ own experiences of them. - Group activity: In their previously assigned small groups, learners decide on the type of event they would like to organise and the aims and objectives of the event. | - Whiteboard to mind-map events |
| 18–19 | Topic B.2 Feasibility of event proposal - Mind-map event ideas. - Purpose of event. - Aims and objectives. - Constraints: budget, venue, resources; human and physical - Success factors – setting goals and targets. |  | - Tutor presentation: Introduce the importance of success factors. - Group activity: In their groups, learners research similar events to the one they have proposed to identify common success factors. | - Tutor presentation and notes - Computers/laptops with internet access |
| 20–21 | Topic B.2 Feasibility measures and critical success factors - Mind-map event ideas. - Purpose of event. - Aims and objectives. - Constraints: budget, venue, resources; human and physical - Success factors – setting goals and targets. |  | - Group activity: Learners prepare a presentation outlining their choice of event, the purpose of the event and the aims and objectives. | - Computers/laptops with presentation software package |
| 22–23 | Topic B.2 Feasibility measures and critical success factors - Mind-map event ideas. - Purpose of event. - Aims and objectives. - Constraints: budget, venue, resources; human and physical - Success factors – setting goals and targets. |  | - Group activity: Learner groups deliver their presentations to the whole class. They should use feedback from the class to help finalise their decision on the viability of the event. | - Computers/laptops with presentation software package - Smartboard |
| Learning aim C: Develop a detailed plan for a business or social enterprise event |  |  |  |  |
| 24–25 | Topic C.1 Event planning and the use of planning tools - Gantt charts. - Critical path analysis. - Online planning tools. | IS | - Tutor presentation: Explain different planning tools and their uses. - Group activity: In their groups, learners decide on an appropriate planning tool to use. They should complete an outline showing the stages of event planning, execution and review. | - Tutor presentation and notes |
| 26–28 | Topic C.2 Factors to be considered, including budgets, resources and contingency planning - Aims and objectives. - Budget: available finance, expected sales figures, banking, cost of resources, expenses such as venue, catering, staff, travel. - Resources: flip charts, Wi-Fi, telephone, display boards, ability to take money, chairs, tables, computer, smart board. - Venue: size of room, facilities available, car parking, access arrangements. - Catering: special consideration of dietary needs. - Legal constraints: contracts, health and safety (risk assessment), negligence liability. - Team working: allocation of tasks, planning meetings. - Insurance, including public liability. - Methods of communication: promotion, letters, invitations. - Contingency planning: ‘what if’ scenarios, e.g. What if the caterers don’t turn up? | IS | - Tutor-led discussion: Discuss and identify all factors that need to be considered when organising an event. - Group activity: Learners allocate tasks to group members and start research into costs, availability etc. | - Whiteboard |
| 29–30 | Topic C.2 Factors to be considered, including budgets, resources and contingency planning - Aims and objectives. - Budget: available finance, expected sales figures, banking, cost of resources, expenses such as venue, catering, staff, travel. - Resources: flip charts, Wi-Fi, telephone, display boards, ability to take money, chairs, tables, computer, smart board. - Venue: size of room, facilities available, car parking, access arrangements. - Catering: special consideration of dietary needs. - Legal constraints: contracts, health and safety (risk assessment), negligence liability. - Team working: allocation of tasks, planning meetings. - Insurance, including public liability. - Methods of communication: promotion, letters, invitations. - Contingency planning: ‘what if’ scenarios, e.g. What if the caterers don’t turn up? | IS | - Tutor presentation: Introduce the topics of contingency planning, and ‘what if’ scenarios. - Group activity: In their groups, learners should discuss possible ‘what if’ scenarios in relation to their events, and produce a contingency plan. |  |
| 31–35 |  | AW | - Assignment writing: Complete assignment 2. | Assignment brief. |
| Learning aim D: Stage and manage a business or social enterprise event |  |  |  |  |
| 36–76 | Topic D.1 Management of the event - Contracts for venue: suppliers, personnel. - Marketing of the event: publicity, advertising, sponsorship, guest list, invitations. - Customer service. - Monitoring procedures to ensure tasks allocated have been completed. - Security and health and safety. - Methods of communication: internally and externally. - Attendee evaluation: prepare, issue and collect questionnaires. Topic D.2 Problem solving - Implementation of contingency plan, e.g. non-delivery of resources. - Customer service issues. - Health and safety issues. | IS | - Tutor activity: Complete observations records/take photographic evidence. - Individual practical activity: Learners should complete their log/diary. - Group practical activity: Within their groups, learners should allocate tasks to individuals to ensure the event is run successfully. - Group practical activity: Groups should hold regular meetings to ensure targets identified in the planning document are being met. Suggestions for resolving problems to be discussed. | - Observation sheets - Camera |
| Learning aim E: Reflect on the running of the event and evaluate own skills development |  |  |  |  |
| 77 | Topic E.1 Evaluation of the event - Review of success: meeting aims and objectives, timing, keeping to budget set, effectiveness of contingency plan. - Analysis of evaluation forms. - Suggestions for improvement. | IS | - Tutor feedback: Give feedback to individual learners on their observed performance throughout staging and running the event. Highlight skills that have been improved/developed. - Individual activity: Learners carry out a self-assessment of their personal skills development. |  |

| 78 | Topic E.2 Review of personal skills development in running the event - Event management. - Employability. - Communication. - Negotiation. - Time management. - Problem solving. - Team working. - Analysis of own skills. | IS | - Tutor feedback: Give feedback to individual learners on their observed performance throughout staging and running the event. Highlight skills that have been improved/developed. - Individual activity: Learners carry out a self-assessment of their personal skills development. |  |
| --- | --- | --- | --- | --- |
| 79–85 |  | AW | - Assignment writing: Learners should complete assignment 3. | Assignment brief. |
| 86–90 |  | AW | - Individual activities: Learners should complete any outstanding work. |  |